## Sheet1
S.No. | Activity | Target date | Status | Remarks/Risk/Issues
1 | Team registration | 2019-03-08 | Completed
2 | Plan, CM, set up github (support) | 2019-03-10
3 | Problem discussion | 2019-03-10
4 | Approach finalization | 2019-03-10
5 | Data sanity, missing values | 2019-03-14
6 | Label encoding discussion | 2019-03-15
7 | First 5 submissions -basic models | 2019-03-16
8 | Next 10 submissions -advance models | 2019-03-19
9 | Upto 25 submissions -advance models | 2019-03-24
10 | Average models/Stack model submission- part 1 | 2019-03-25
11 | Average models/Stack model submission- part 2 | 2019-03-27
12 | Final discussion on the approach and model selection | 2019-03-29
13 | Finalize top 5 models | 2019-04-04
14 | Submission last date | 2019-04-07
15 | Final 2 file Submission | 2019-04-14
Working Time: Weekdays (1-2 hours, 9 am-11 am depending upon availability) Weekends (4-6 hours depending upon discussion)